## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Risk Register
| Table 1 | Risk Register
Scale
| Table 1 | Scale

## Risk Register
RISK REGISTER TEMPLATE
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER | KEY
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | LEVEL
Data security breach compromising user information | User data could be exposed, leading to legal issues and loss of trust | 4 | 5 | 20 | Implement strong encryption and conduct regular security audits | IT Security Lead | 1
High competition affecting user acquisition | Reduced market share and slower business growth | 3 | 4 | 12 | Focus on unique features, provide incentives, and strengthen marketing | Marketing Manager | 2
Integration issues with third-party services | Project delays and potential system failures | 3 | 3 | 9 | Ensure use of reliable APIs and plan for fallback solutions | Integration Lead | 3
Scalability issues during high traffic | Service disruptions and poor user experience | 4 | 4 | 16 | Use scalable cloud services and optimize code for efficiency | DevOps Engineer | 4
Delays in development | Project timeline extension and increased costs | 3 | 4 | 12 | Adopt Agile methods with regular progress checks | Project Manager | 5
CLICK HERE TO CREATE IN SMARTSHEET

## Scale
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
I M P A C T